## Sheet1
Waterfall Gantt Chart Template
Project Title: | Yosemite, eCommerce company |  | Start Date: |  | 2022-09-03
Project Manager: | Fabian Stigler |  | Estimated Completion Date: |  | 2022-12-17
 | time axis 2022-09-05 to 2022-12-16
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2022-09-05: WEEK 1; 2022-09-12: WEEK 2; 2022-09-19: WEEK 3; 2022-09-26: WEEK 4; 2022-10-03: WEEK 5; 2022-10-10: WEEK 6; 2022-10-17: WEEK 7; 2022-10-24: WEEK 8; 2022-10-31: WEEK 9; 2022-11-07: WEEK 10; 2022-11-14: WEEK 11; 2022-11-21: WEEK 12; 2022-11-28: WEEK 13; 2022-12-05: WEEK 14; 2022-12-12: WEEK 15
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Storefront on the platform | bar: WEEK 9 M to WEEK 15 F
Kickoff Meeting | Mama Stefano, Moe, Lou, Aliyah | 2022-09-05 | 2022-09-06 | 2 | bar: WEEK 1 M to WEEK 1 T
build storefront | Mama Stefano, Moe | 2022-09-07 | 2022-09-19 | 9 | bar: WEEK 1 W to WEEK 3 M
Status Report | Mama Stefano, Moe | 2022-09-19 | 2022-09-19 | 1 | bar: WEEK 3 M
Input Inventory Data | Mama Stefano, Lou | 2022-09-20 | 2022-09-27 | 6 | bar: WEEK 3 T to WEEK 4 T
Status Report | Mama Stefano, Lou | 2022-09-27 | 2022-09-27 | 1 | bar: WEEK 4 T
Train Stefano’s on platform | Aliyah | 2022-09-28 | 2022-09-28 | 1 | bar: WEEK 4 W
Documenting knowledge | Mama Stefano, Moe, Lou, Aliyah | 2022-09-29 | 2022-09-30 | 2 | bar: WEEK 4 Tr to WEEK 4 F
social media integration | bar: WEEK 9 M to WEEK 15 F
Kickoff Meeting | Aliyah, Taylor, Junior Stefano | 2022-09-30 | 2022-10-03 | 4 | bar: WEEK 4 F to WEEK 5 M
Create social media channels | Taylor | 2022-10-04 | 2022-10-07 | 4 | bar: WEEK 5 T to WEEK 5 F
Status Report | Taylor | 2022-10-07 | 2022-10-07 | 1 | bar: WEEK 5 F
Build social media integration | Aliyah | 2022-10-10 | 2022-10-13 | 4 | bar: WEEK 6 M to WEEK 6 Tr
Status Report | Aliyah | 2022-10-13 | 2022-10-13 | bar: WEEK 6 Tr
Train Stefano’s on social media use | Junior Stefano | 2022-10-14 | 2022-10-14 | 1 | bar: WEEK 6 F
Documenting knowledge | Aliyah, Taylor, Junior Stefano | 2022-10-17 | 2022-10-18 | 2 | bar: WEEK 7 M to WEEK 7 T
Recommendation engine | bar: WEEK 9 M to WEEK 15 F
Kickoff Meeting | Aliyah, Mama Stefani, Papa Stefano, me | 2022-10-19 | 2022-10-20 | 2 | bar: WEEK 7 W to WEEK 7 Tr
Build recommendation engine | Aliyah | 2022-10-21 | 2022-10-27 | 5 | bar: WEEK 7 F to WEEK 8 Tr
Status Report | Aliyah | 2022-10-27 | 2022-10-27 | 1 | bar: WEEK 8 Tr
Create Automated Sales Report | Mama Stefano | 2022-10-28 | 2022-10-31 | 2 | bar: WEEK 8 F to WEEK 9 M
Status Report | Mama Stefano | 2022-10-31 | 2022-10-31 | 1 | bar: WEEK 9 M
Engage stakeholders | Papa Stefano, me | 2022-11-01 | 2022-11-02 | 2 | bar: WEEK 9 T to WEEK 9 W
Documenting knowledge | Aliyah, Mama Stefani, Papa Stefano, me | 2022-11-03 | 2022-11-03 | 1 | bar: WEEK 9 Tr
Add Phase/Milestone As Needed | bar: WEEK 9 M to WEEK 15 F
Build social media integration | Aliyah